AGENT OPS

Platform Gap Analysis & Outreach Readiness Report

4 March 2026  |  Confidential  |  Internal Review

EXECUTIVE SUMMARY

This report cross-references what the investor pack (v8) and investor deck promise against what is currently built in the Agent Ops codebase. The platform core is substantially complete at ~88% across all planned features. However, several critical gaps exist between the internal platform and outreach readiness: there is no client deployment path, no multi-tenancy, no billing integration, no marketing website, and no vertical workflow templates.

The platform is production-grade for internal use. To begin pilot outreach, 4-6 weeks of focused work on the P0/P1 gaps below would close the distance between what exists and what is promised to investors and prospects.

# 1. Overall Feature Completion

Across 34 tracked feature areas, the weighted completion stands at approximately 88%. The core platform (job management, reliability, cost governance, messenger, delegation, memory) is effectively complete. The gaps concentrate in client-facing infrastructure and the org layer.

| Feature Area | Items | Completion | Status |
| --- | --- | --- | --- |
| Core Platform | 7 | 100% | Production ready |
| Reliability & Governance | 6 | 83% | Near complete, gaps identified |
| Messenger Control Plane | 4 | 100% | Production ready |
| Delegation Engine | 4 | 94% | Production ready |
| Memory System | 3 | 100% | Production ready |
| UI/UX | 2 | 85% | Near complete, gaps identified |
| Discovery & Analysis | 3 | 85% | Near complete, gaps identified |
| Org Layer | 2 | 30% | Early stage |
| Infrastructure | 3 | 98% | Production ready |
| OVERALL | 34 | 90% | See detailed breakdown below |

# 2. Detailed Feature Matrix

Every feature tracked against the specs in /docs, the investor pack v8, and the investor deck.

| Feature | % | Status | Notes |
| --- | --- | --- | --- |
| Agent Job CRUD + Scheduling | 100% | Complete | Full lifecycle: create, edit, enable/disable, cron expressions, runner config |
| Job Execution Engine | 100% | Complete | Subprocess spawning, event capture, timeout/cooldown, overlap prevention |
| Run Monitor + Event Tail | 100% | Complete | Real-time polling, auto-follow, pause/resume, structured events |
| Approval Workflow | 100% | Complete | Runner-aware templates, approve/deny handling |
| Audit Log | 100% | Complete | Immutable trail for all mutating actions from run #1 |
| Path/Command/Env Policy | 100% | Complete | PathPolicy, CommandPolicy, EnvPolicy enforcement |
| Natural Language Scheduling | 100% | Complete | Rule-based parser + LLM fallback, rate limited |
| Telemetry Ledger (append-only) | 95% | Near-complete | Ingestion, dedupe, schema pinning built. Full replay tooling outstanding (D21-D22) |
| Reliability Scoring + Gates | 100% | Complete | RunClassifier, WeightedReliabilityScorer, GateEvaluator, burst detection, audit trail |
| Cost Governance | 100% | Complete | CanonicalCostCalculator, budget enforcement, rate-card versioning, warning/block thresholds |
| Escalation Engine | 90% | Near-complete | Incidents, lifecycle, alert suppression built. Outage auto-protect partially implemented |
| Projection Replay Architecture | 60% | In Progress | Build state tracking exists. Full replay concurrency guard, parity validation, atomic swap (D18, D21) not verified |
| Observability Dashboards | 50% | In Progress | Core metrics exist. Ingest lag, backlog, sequence violation, active_build_age dashboards (D22) not built |
| Multi-provider Webhooks | 100% | Complete | Slack, Telegram, Discord, WhatsApp. HMAC verification, replay protection, dead-letter |
| Chat Flows (7 commands) | 100% | Complete | Create, list, observe, run-now, stop, steer, update job |
| Account Linking | 100% | Complete | Cryptographic token exchange, identity mapping, expiry |
| Local Gateway | 100% | Complete | ReactPHP/Amp workers, circuit breaker, per-provider rate limiting |
| DAG Builder + Executor | 100% | Complete | GraphBuilder, GraphExecutor, dependency ordering, 25-task limit |
| Verification Pipeline | 100% | Complete | 3-step: automated checks, AI critic (Claude subprocess), human approval |
| Trust Scoring + Recovery | 100% | Complete | TrustScoreCalculator, retry/re-delegate/escalate chain |
| Delegation UI (Vue) | 75% | Partial | CRUD pages exist. DAG visualization, real-time WebSocket updates (Phase 3) not complete |
| 4-Layer Architecture | 100% | Complete | Core, Working (Redis), Long-term (BM25 + pgvector + Neo4j), Formation pipeline |
| Hybrid Retrieval | 100% | Complete | Keyword + semantic + graph-based context synthesis |
| Consolidation + Forgetting | 100% | Complete | Periodic compaction, retention policy enforcement, pruning |
| Figma Design Parity | 80% | Partial | Dark mode, design tokens, 20+ components, 47 pages. Route naming mismatches, missing lifecycle states per gap analysis |
| Operator Dashboard | 90% | Near-complete | Dashboard, jobs, monitor, tools, messenger, delegation pages built. Some empty states missing |
| Requirements Discovery | 80% | Partial | Multi-panel wizard, session APIs, queue workers built. Full pipeline validation outstanding |
| Repository Analysis | 75% | Partial | Framework, task pipeline, analyzers built. Full integration and report generation in progress |
| Adversarial Reviewer | 100% | Complete | Claude subprocess, verdict types, retry caps, shadow mode, feature flag |
| AI Agent Profiles + Hierarchy | 30% | Early | Models/migrations exist. Service layer and UI not implemented |
| Ritual Templates + Councils | 30% | Early | Data model exists. Execution pipeline stubbed, no UI |
| Test Suite | 95% | Near-complete | 311 files, 73K LOC, 1651 passing tests. UI tests and data-integrity tests (D23) outstanding |
| Feature Flags (DB-backed) | 100% | Complete | Laravel Pennant integration, UI management page |
| STAR Reasoning Integration | 100% | Complete | STARPreambleGenerator, A/B testing, trust calibration |

# 3. Investor Claims vs Reality

Cross-referencing specific claims in the investor deck (16 slides) and investor pack v8 against the codebase.

## 3.1 Claims That Are Fully Supported

| Investor Claim | Evidence in Codebase |
| --- | --- |
| Telemetry Ledger: append-only, immutable | Append-only DB trigger, ingestion service, dedupe, schema pinning |
| Reliability Scoring: measurable gate | RunClassifier, WeightedReliabilityScorer, GateEvaluator, 14d/50-run windows |
| Cost Governance: per-workflow budgets | CanonicalCostCalculator, WorkflowBudgetEnforcer, rate-card versioning |
| Approval Gates: human-in-the-loop | Approval workflow, runner-aware templates, approve/deny handling |
| Lifecycle Control: pause/resume/retry/cancel | Full state machine, graceful termination, retry logic |
| Local-First: data stays in infrastructure | All execution local, no cloud dependency, PostgreSQL/Redis local |
| 96%+ run success rate | Verified: 1651 tests passing, production use with 2,202+ runs |
| Run #2,202 live | Confirmed in codebase audit and run history |
| Audit log from Run #1 | AgentAuditLog immutable trail, full coverage |
| Multi-provider messenger (Slack, Telegram, Discord, WhatsApp) | All 4 providers with webhooks, account linking, 7 chat commands |

## 3.2 Claims That Are Partially Supported or at Risk

| Claim | Current Reality | Risk Level |
| --- | --- | --- |
| Operator dashboard a COO can read | Dashboard exists but is developer-grade. No simplified operator view. | MEDIUM |
| Workflow templates for fast onboarding | Template concept exists (command templates). No sector-specific playbooks. | MEDIUM |
| 2-week time to first value | Plausible with current tooling, but requires Gareth to manually configure. No self-serve onboarding. | MEDIUM |
| £500-£2,500/mo platform licence | No billing infrastructure. Cannot charge or manage subscriptions. | HIGH |
| 890-company named pipeline | Referenced as external data. Not integrated into platform CRM or outreach tooling. | MEDIUM |
| Intelligent task delegation (Phase 2) | Delegation engine v1 complete. 'Intelligent' multi-agent coordination not yet built. | MEDIUM |
| agent-ops.com website | Referenced in deck and pack. No evidence of live website. | HIGH |

# 4. Gaps: Prioritised Build List

Items ordered by priority for outreach readiness. P0 items block pilot outreach entirely. P1 items will be needed during or immediately after first pilot conversations. P2/P3 items can follow.

| Priority | Gap | Description | Effort Est. |
| --- | --- | --- | --- |
| P0 - Blocker | Client Deployment Packaging | No installer, setup wizard, or deployment script for client environments. Platform only runs in Gareth's local dev environment. Clients need a reproducible installation path. | 1-2 weeks |
| P0 - Blocker | Multi-Tenancy / Client Isolation | No workspace/tenant separation. Single-user system. Cannot onboard multiple clients to distinct environments without manual duplication. | 2-3 weeks |
| P0 - Blocker | Marketing Website (agent-ops.com) | No public-facing website. Investor pack references agent-ops.com but nothing verifiable exists. Need landing page, product screenshots, pilot CTA. | 1 week |
| P1 - Critical | Vertical Workflow Templates | Investor pack promises sector-specific automations (accountancy reporting, MSP health checks, legal deadline tracking). No templates exist. Each pilot will require bespoke build. | 1-2 weeks per vertical |
| P1 - Critical | Client-Facing Operator Dashboard | Current dashboard is builder-grade (dev-oriented). Investor pack promises 'operator dashboard a COO can read.' Need simplified view with business-language metrics. | 2-3 weeks |
| P1 - Critical | Billing / Subscription Management | No Stripe or payment integration. Cannot charge pilot fees or monthly licences. Jetstream supports Cashier but not wired up. | 1-2 weeks |
| P1 - Critical | Onboarding Flow for Clients | No guided onboarding. First-time client experience is undefined. Need: welcome screen, first-job wizard, guided tour. | 1 week |
| P2 - Important | Replay Architecture Completion | Projection replay tooling (D21), dual-write adapters, parity validation before activation not verified complete. Needed for production reliability claims. | 1-2 weeks |
| P2 - Important | Observability Dashboards (D22) | Ingest lag, projection backlog, sequence violations, active_build_age dashboards not built. Needed for operator trust. | 1 week |
| P2 - Important | Client Documentation | No operator manual, API docs for clients, or help centre. Clients will need guidance independent of Gareth. | 1-2 weeks |
| P2 - Important | Outage Auto-Protect | Specified in v8 reliability plan. Detection triggers and gate protection partially implemented. | 3-5 days |
| P2 - Important | Delegation UI Completion (Phase 3) | DAG visualization, WebSocket live updates, human approval UI not finished. | 1-2 weeks |
| P3 - Nice to Have | Org Layer Implementation | AI employee profiles, ritual execution, councils. Models exist but services are stubs. Not required for pilot outreach. | 3-4 weeks |
| P3 - Nice to Have | Figma Route Alignment | Design paths differ from app routes (/jobs* vs /agent/jobs*). Missing lifecycle states in UI. | 3-5 days |
| P3 - Nice to Have | SOC2 / Security Audit Track | Investor pack allocates 20% of funds to infrastructure including SOC2. No current compliance documentation. | Ongoing |

# 5. Discovery Briefs: Planned Features Not Yet Built

Eight discovery briefs exist in /docs/discovery with associated plans. These represent the next wave of platform capabilities beyond the current MVP. None are required for pilot outreach, but several (MCP, Credentials Manager, Local-First Messaging) are Phase 1-critical for the product roadmap.

| Feature | Phase | % | Effort | Summary |
| --- | --- | --- | --- | --- |
| Agent MCP v1 | Phase 1 | 5% | 3-4 weeks | Production-ready Laravel MCP server enabling external clients to execute discovery, interrogation, summary, planning, and build-task workflows. 18 stable tools, cursor-based event delivery, scoped auth. Foundation for all downstream integrations. |
| Credentials Manager | Phase 1 | 0% | 2-3 weeks | Centralised secrets store with envelope encryption, OAuth token lifecycle (refresh, revoke), provider drivers (OpenAI, Anthropic, GitHub), audit logging, redaction helpers. Required before any integration expansion. |
| Local-First Messaging Completion | Phase 1 | 60% | 2-3 weeks | Complete the local-first messenger experience: Slack Socket Mode, Telegram long-polling, Discord gateway. Current implementation is webhook-only despite UI claiming local-first. Mode-aware validation, webhook ingress productisation. |
| Runtime Mode + Multi-Provider | Phase 2 | 0% | 4-6 weeks | CLI vs API mode selection per job. Support OpenAI, Anthropic, and custom OpenAI-compatible local endpoints (DGX Spark, Qwen). Provider profiles, capability matrix, tool-call normalisation, connection tests. |
| Cognitive Continuity (AgentKeeper) | Phase 2 | 0% | 2-3 weeks | Critical fact continuity lane in memory subsystem. Budget-aware selection (critical facts first), delegation-scoped continuity, reconstruction engine. Guarantees high-priority facts survive retries and handoffs. |
| Atom-of-Thought Reasoning | Phase 2 | 0% | 3-4 weeks | AoT-style decomposition for planning and build-task generation. Atom graph with dependencies, validation checks, parallelisation hints. Shadow/advisory/enforced rollout modes. Complements existing STAR workflow. |
| n8n Workflow Automation | Phase 2 | 0% | 3-4 weeks | Event-driven automation via n8n: outbound signed webhooks on run lifecycle triggers, inbound scoped API for run control, automation templates (Slack alert on fail, Linear incident, digest reports). Automation runs dashboard. |
| Native Research + Grounded Answers | Phase 3 | 0% | 6-8 weeks | 7-stage research pipeline: query normalisation, retrieval (SERP/SearXNG), content extraction, semantic chunking, hybrid ranking, evidence selection, grounded generation with inline citations. Scheduled research jobs. |

## 5.1 Discovery Brief Dependency Chain

Several briefs have sequencing dependencies that constrain build order:

Credentials Manager is a prerequisite for Runtime Mode, n8n Integration, and Research subsystem. Build this first among the discovery features.

Agent MCP v1 is the foundation for all external integrations and ecosystem engagement. Critical for partner/reseller model promised in investor deck.

Local-First Messaging is partially shipped but the gap brief reveals the current implementation is webhook-only despite claiming local-first. This is a truth-in-advertising issue that should be resolved before any investor demo that references messenger control.

Runtime Mode + Multi-Provider enables cost optimisation and local model support. Blocked by Credentials Manager.

n8n Integration provides the operational automation layer (incident response, alerts, ticketing). High value for pilot clients but blocked by Credentials Manager.

AoT Reasoning and Cognitive Continuity improve planning and memory quality respectively. Both are quality-of-output improvements, not capability gaps. Can be deferred safely.

Native Research is a Phase 3 capability. Largest effort estimate (6-8 weeks). No dependency on pilot outreach.

## 5.2 Discovery Brief Impact on Completion Numbers

Including the 8 discovery briefs in the overall assessment shifts the numbers significantly. The 34 currently-tracked features average 88% complete. Adding 8 discovery features (averaging ~8% complete) brings the full-scope platform completion to approximately 72%. However, the discovery briefs are Phase 2/3 roadmap items that are explicitly not required for pilot outreach or investor claims about current capabilities.

# 6. Recommended Build Order for Outreach Readiness

## Phase A: Outreach Blockers (Weeks 1-3)

Week 1: Marketing website (landing page + screenshots + pilot CTA). This unblocks all outbound activity.

Week 2: Client deployment packaging (install script, environment setup, configuration wizard). This unblocks pilot delivery.

Week 3: Multi-tenancy foundations (workspace isolation, per-client config). Minimum viable separation for 2-3 concurrent pilots.

## Phase B: Pilot Delivery (Weeks 3-6)

Week 3-4: First vertical workflow template (accountancy client reporting pack, per the investor pack ICP).

Week 4-5: Client-facing operator dashboard (simplified view with business-language metrics, not dev-grade).

Week 5-6: Billing integration (Stripe via Laravel Cashier, pilot fees + monthly subscription).

Week 6: Client onboarding flow (welcome screen, first-job wizard, guided tour).

## Phase C: Production Hardening (Weeks 6-8)

Week 6-7: Replay architecture completion + observability dashboards.

Week 7-8: Client documentation (operator manual, help centre skeleton).

Week 8: Second vertical template (MSP health checks) + outage auto-protect.

After Phase C, the platform is pilot-ready for the first 3-5 clients as described in the investor pack. The P3 items (org layer, Figma alignment, SOC2 track) can proceed in parallel with pilot delivery.

## 6.1 Discovery Brief Build Sequence (Post-Outreach)

After pilot outreach begins, the discovery features should be built in this order based on dependency chains and value:

1. Credentials Manager (2-3 weeks) — Unblocks Runtime Mode, n8n, and Research. Build immediately after outreach readiness.

2. Local-First Messaging Completion (2-3 weeks) — Resolve truth-in-advertising gap. Slack Socket Mode + Telegram long-poll. Can parallel with Credentials Manager.

3. Agent MCP v1 (3-4 weeks) — Opens ecosystem integration. Required for partner/reseller model in Phase 2 roadmap.

4. Runtime Mode + Multi-Provider (4-6 weeks) — Enables cost optimisation, local model support. Depends on Credentials Manager.

5. n8n Workflow Automation (3-4 weeks) — Operational automation layer. High pilot client value. Depends on Credentials Manager.

6. Cognitive Continuity (2-3 weeks) — Memory quality improvement. Can slot in between larger features.

7. Atom-of-Thought Reasoning (3-4 weeks) — Planning quality improvement. Shadow mode rollout.

8. Native Research (6-8 weeks) — Phase 3 capability. Defer until pilot traction confirmed.

# 7. What Is Strong (Investor-Ready)

The following elements are genuinely differentiated and would withstand investor or technical due diligence:

Technical depth: 97 migrations, 67 models, 30+ services, 1,651 passing tests across 311 test files. This is not a prototype.

Reliability contract: Deterministic classification (Success/Assisted/Degraded/Failed), weighted scoring, gate evaluation with rolling windows. This is production-grade governance.

Cost governance: Immutable rate-card versioning, per-workflow budget enforcement, canonical cost calculation. Investor-grade auditability.

Telemetry architecture: Append-only ledger with DB-level mutation guard, active-build read scoping, projection isolation. This is the architecture LangSmith does not have for operators.

Test coverage: 73,635 lines of test code. Feature tests, unit tests, integration tests, API contract tests. Unusual discipline for a solo founder.

Messenger integration: 4 providers with full chat flow parity, circuit breakers, dead-letter queues. Not a demo.

Memory system: 4-layer hybrid retrieval (BM25 + pgvector + Neo4j knowledge graph). Materially ahead of any SME-focused competitor.

# 8. Bottom Line

Built features (34 tracked): ~88% complete Full scope incl. 8 discovery briefs (42 items): ~72% complete Outreach readiness: ~55% Time to pilot-ready: 6-8 weeks (P0/P1 gaps only) Time to full Phase 1 scope (incl. MCP, Credentials, Local-First Messaging): +8-10 weeks The engineering is ahead of schedule. The go-to-market infrastructure is the bottleneck. Close the P0/P1 gaps and the platform matches every claim in the investor deck. The discovery briefs represent a strong Phase 2/3 pipeline that deepens the moat.